## TIMELINE
YEAR | MONTH | DATES | CONFIRMED | CLOSED | INSTITUTION | CONTACT PERSON | SCHOOL WORKSHOPS | PUBLIC WORKSHOPS | CAPACITY | INSTALLATION | WORKSHOPS
2025 | april |  | TRUE | TRUE | Grunskóli Bíldudal | liljarut@vesturbyggd.is | 1 | 1 | 15 | KB | KB
2025 | april |  | TRUE | TRUE | Grunnskóli Ísafjörður | gudnyst@isafjordur.is | 5 | 1 | 85 | KB | KB
2025 | april |  | TRUE | TRUE | Leikskóli Hagaborg, Drekaland | Erna.Gudlaugsdottir@reykjavik.is | 2 | 0 | 20 | KB | KB
2025 | september | 27.9. | TRUE | FALSE | Móðurmál | renatapeskova@yahoo.com | 3 | 0 | 45 | KB | KB
2025 | november | 17.-29.11. | TRUE | FALSE | Borgarbókasafn Spöngin | ingibjorg.osp.ottarsdottir@reykjavik.is | 10 | 2 | 180 | KB, ?,? | KB, ?,?
2025-06-01 | june 2026? | june? | FALSE | FALSE | Kötlusetur | kotlusetur@vik.is | 1 | 1 | 30 | KB | KB
2026 | apríl | 1 week | TRUE | FALSE | Listasafn Íslands | ragnheidur.vignisdottir@listasafn.is | 5 | 1 | 90 | KB, ?,? | KB, ?,?
2026 | spring | may? | FALSE | FALSE | Fjarðarbyggð EGS or Neskaupstaður | thorhildur.tinna@fjardabyggd.is | 5 | 1 | 90 | KB, ?,? | KB, ?,?
2026 | autumn | september? | FALSE | FALSE | Norðurland - Partner TBF | safnahus@husmus.is / safn@sild.is | 2 | 1 | 45 | KB | KB
2026 | autumn | october likely, will confirm in october, maye possible more funding and more locations in Vesturland | TRUE | FALSE | Vesturland - Borgarnes | sigursteinn@ssv.is | 2 | 1 | 45 | KB | KB
2027 | spring | 1.-5.2. | TRUE | FALSE | Bókasafn Hafnarfjarðar | unnurmoller@hafnarfjordur.is | 5 | 1 | 90 | KB, ?,? | KB, ?,?
INSPO DATES
2026 |  | 2025-04-22 |  |  | Earth Day
2026 |  | 2026-02-15 |  |  | International whale day
2026 |  | 2025-06-08 |  |  | International ocean day
2026 |  | 2025-06-07 |  |  | Sjomannadagur

## TODO
WHAT | DEADLINE | WHO | DETAIL | BUDGET | CHECK
communication Móðurmál | 2025-06-01 | KB | presentation and explanation message to Móðurmál groups | 0 | TRUE
communication Spöngin | 2025-06-01 | KB | dates | 0 | TRUE
communication Listasafn | 2025-06-01 | KB | dates | 0 | TRUE
communication Kötlusetur | 2025-06-01 | KB | dates | 0 | TRUE
communication Hafnarfjörður | 2025-06-01 | KB | dates | 0 | TRUE
communication Fjarðarbyggð | 2025-08-01 | KB | dates | 0 | FALSE
communication Vesturland | 2025-06-01 | KB | dates | 0 | TRUE
Norðurland - get a partner | 2025-06-01 | KB | dates | 0 | TRUE
refresh Kötlusetur | 2025-06-01 | KB | dates | 0 | FALSE
Spöngin schools communication | 2025-09-01 | KB | dates | 0 | FALSE
midi button & scanner triggering | 2025-08-01 | OH?, ÞE? | also refresh trigger, screens for holo and projection | 10000 material, 40000 work | FALSE
optimization of particles and player | 2025-08-01 | OH? | touch player, random particle generation make sure for all to appear, some extra interaction or game functionality, video simplify maximum effectiveness, better interaction | 100000 work | FALSE
scanner box and hologram | 2025-10-01 | KB, ÞE? |  | 25000 material, 50000 work | FALSE